## Sheet1
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18/12/2020 | Computer Crashing & Losing the data | My Laptop might crash for various reason. |  | / | / |  |  | This will impact the project as I would lose all progress made with this laptop. | N/A | I was given a QA community Laptop as well and this will allow me to switch from my personal Laptop to the QA one if nessessary as my personal laptop is what I'm currently using. I would then fork my repository from github and continue the work on there | Github | https://github.com/MohamudMussa
2 | 18/12/2020 | Covid-19 | Contract Covid-19 or a family member getting Covid-19 |  | / |  | / |  | This can impact the project in many ways. One being that it would affect my ability to work on the project. If covid was to happent to a family member I'd need to take care of them whilst working on this project too. | A week | While self isolating I can still use my laptop although I might need time to recover.
3 | 19/12/2020 | Schedule Risk | Not completing the project on time | / |  |  |  | / | Wrong time estimation Resources are not tracked properly. All resources like staff, systems, skills of individuals, etc. Failure to identify complex functionalities and time required to develop those functionalities. Unexpected project scope expansions. | 2 Weeks overall project sprint | On agile projects the team is heavily involved in planning and estimating through activities such as XP's planning game and Wideband Delphi workshops. By working in short increments the true velocity of the team quickly emerges and is visible to all stakeholders who are now more closely involved in the project. In short, the true progress is hard to hide and quickly revealed, giving feedback to the stakeholders. | Project Name: | QA-Project1
4 | 2020-01-01 | Git Merge Conflics | I could have a merge conflicts or overwrite by merging incorrectly. | / |  |  |  | / | This could impact the project majorly as I would have to start from where the overwrite took place. I would also need to resolve a conflict merge issue | A day / 2 | Constantly update my github by doing comits regularly. Also | Project Description:
5 | 2020-02-01 | Application crashing | Main project application crashing due to issues caused by deleing files or removing vital code |  | / |  |  | / | This can really effect the project as small code with issues can lead to the whole program not working | A day / 2 | Build in small steps, this will allow me to correct myself when I need to. I'd also know when or what is causing the issue as I will be building in increments | Project Owner: | Mohamud Mussa
6
7 | [11 empty] | Risk Level | Colour
8 | [11 empty] | Low
9 | [11 empty] | Medium
10 | [11 empty] | High
11
12 | [11 empty] | Medium
13 | [11 empty] | High
14
15
16
17
18
19
20